## Slide 1
MAY 2026
— THE BUILD-OUT
Roadmap
5 SECTIONS
~100 TASKS
27 – 38 WEEKS
Notes: Welcome everyone. Today I want to walk you through the full build-out plan for our hotel booking platform. This isn't just databases — it's the whole stack. We've mapped roughly one hundred tasks across five tracks: database schema, admin CRUD, frontend components, public APIs, and the page integrations that pull it all together. I've grouped everything into a sequenced roadmap so you know what we're building, in what order, and how the tracks depend on each other.

## Slide 2
— OVERVIEW
Five Sections, one platform.
From schema to shipped pages — backend, frontend, and the seam between them.
Section 1
Database Schema
23 tables across 4 phases — hotels, inventory, geo, marketing, users, system.
23 TABLES
Section 2
Admin CRUD
Operations admin — list, create, edit, delete for every table.
23 MODULES
Section 3
Frontend Components
Site chrome, home, hotel detail, search results — reusable library.
33 COMPONENTS
Section 4
Public APIs
Read endpoints feeding the public website — search, detail, discovery.
19 ENDPOINTS
Section 5
Page Integration
Home, search results, single hotel — assembly and routing.
3 PAGES
02 / 22
HOTEL PLATFORM
Notes: Quick map. Five tracks. Track one is the database schema — twenty-three tables. Track two is the admin CRUD layer that lets the operations team manage those tables. Track three is the frontend component library — header, footer, hotel cards, filters, the works. Track four is the public APIs that feed the website. Track five is the three page integrations that wire everything together — home, search results, and single hotel. Tracks one and two are pure backend; track three is pure frontend; tracks four and five are the seam between them.

## Slide 3
HOTEL PLATFORM / SECTION 1
— Section ONE
Database schema.
The structure consists of 23 tables. The first section serves as the backbone or the core of the system, and all other tables and components depend on it and branch out from it in a cascading manner.
Hotel Core
Hotel · Hotel_Type Hotel_Group · Hotel_Rules Hotel_Tag
5 TABLES
Inventory & Rates
Room_Type · Availability Rate_Plan · Provider
4 TABLES
Facilities & Geo
Facility · Group_Facility Facility_Hotel · Tag Location · Landmark · Category
7 TABLES
Marketing & System
Banner · Promotion · QA Users · Member · Comment Setting
7 TABLES
[ IMAGE_02 ]
Schema diagram
Minimal line illustration of an entity-relationship diagram with five connected boxes, single-stroke architectural style, ochre and dark-ink lines on warm cream paper.
03 / 22
Notes: Track one — the database schema. Twenty-three tables, grouped into four phases by domain. Hotels and rules. Rooms, rates, and inventory. Facilities and geography. And finally marketing, users, and system configuration. I'll go through each phase on the next slides. Worth noting up front: phase one is a hard dependency for almost everything else, so we land it first.

## Slide 4
HOTEL PLATFORM / SECTION 1
01
— PHASE ONE
Hotel Core.
The spine of the system — every other domain hangs off these five tables.
5 Tables
Hotel
Core record per property — name, address, status.
Hotel Type
Property types — boutique, resort, apartment.
Hotel Group
Chains and brand families — Parsian, Homa.
Hotel Rules
Check-in, cancellation, age and child rules.
Hotel Tag
Pivot — attaches descriptive tags to any hotel.
04 / 22
Notes: Phase one — Hotel Core. Five tables. Hotel is the root record. Hotel Type categorizes properties — boutique, resort, apartment. Hotel Group captures chains like Parsian or Homa. Hotel Rules holds check-in policies and cancellation terms. And Hotel Tag is the join table for descriptive tags. This is the spine — week one priority.

## Slide 5
HOTEL PLATFORM / SECTION 1
05 / 22
02
— PHASE TWO
Rooms, rates & inventory.
The booking engine starts here — date-by-date availability, pricing schemes, and external feeds.
4 Tables
Room Type
Bookable units — single, double, suite, occupancy and bed config.
Availability
Date · room · count · price. The hot table — every search hits it.
Rate Plan
Sale conditions — bed-and-breakfast, refundable, packages.
Provider
Source registry for ingested availability and rate feeds.
Notes: Phase two — Rooms, Rates and Inventory. Four tables. Room Type defines what's bookable. Availability is the high-volume table — date by date, room by room, count and price. This will get hammered on every search query so we index it carefully. Rate Plan layers pricing schemes on top — bed-and-breakfast, refundable, packages. Provider tracks where each external feed of availability and rates came from.

## Slide 6
HOTEL PLATFORM / SECTION 1
03
— PHASE THREE
Facilities & geography.
Descriptive layer plus location data. Both run in parallel after phase one.
7 Tables
Facility
Master amenity list — wifi, pool, parking.
Group Facility
Buckets — room, common area, sports.
Tag
Editorial tags — luxury, budget, family.
Location
Country · province · city · neighborhood tree.
Landmark
Airports, metro, attractions near each hotel.
Category
Cross-domain taxonomy — applies to hotels and cities.
06 / 22
Notes: Phase three combines facilities and geography. Seven tables. On the facility side we have the master Facility list, the Group Facility buckets, the Facility Hotel pivot, and the editorial Tag table. Geography gives us Location for the country-province-city-neighborhood hierarchy, Landmark for nearby points of interest, and Category for the cross-cutting taxonomy that applies to both hotels and cities. None of these block phase two, so we can run them in parallel.

## Slide 7
HOTEL PLATFORM / SECTION 1
04
— PHASE FOUR
Marketing, users & system.
Closing out the schema — content, identity, reviews, and configuration.
7 Tables
Banner
Promotional banners — homepage hero, search inserts.
Promotion
Campaigns — discount codes, seasonal deals.
QA
FAQ and user-submitted Q&A.
Users
Internal staff — admins, operators, editors.
Member
Customer accounts — travelers who book.
Comment
Reviews and ratings — feeds search ranking.
Setting
Global configuration — payment gateways, social links, contact info, feature flags. Editable without redeploy.
07 / 22
Notes: Phase four ties off the schema with marketing, users, and system tables. Seven tables. Banner and Promotion drive the marketing surfaces. QA holds FAQ and user-submitted questions. Users is the internal staff identity stack; Member is the customer-side stack — kept separate. Comment captures reviews and ratings, which feeds search ranking. And Setting holds global configuration that product can edit without a redeploy.

## Slide 8
HOTEL PLATFORM / SECTION 1
— DATABASE SCHEMA PHASING
Database schema
In essence, parts of the database structure (tables, relationships, constraints, etc.) are designed and implemented
P1 · Wk 1
Hotel Core
Hotel, Hotel Type, Hotel Group, Hotel Rules, Hotel Tag
5 TABLES
P2 · Wk 1
Rooms, rates & inventory
Room Type, Availability, Rate Plan, Provider
4 TABLES
P3 · Wk 1
Facilities & geography.
Facility, Group Facility, Location, Landmark, Tag, Category
6 TABLES
P4 · Wk 2 – 3
Marketing, users & system.
Banner, Promotion, QA, User, Member, Comment, Setting
7 TABLES
08 / 22
Notes: How we sequence the CRUD work. We bundle CRUD modules in the same phases as their underlying tables — Hotel CRUD with Hotel DB, Room CRUD with Room DB, and so on. The advantage: the operations team gets a usable admin tool for each domain as soon as the table is migrated. They start seeding real data while we build the next phase. By the time phase four DBs land, the ops team has been live for weeks.

## Slide 9
HOTEL PLATFORM / SECTION 2
— SECTION TWO
Admin CRUD layer.
One CRUD module per table. Standard list / create / edit / delete with validation. Ships in lockstep with the underlying schema.
Hotel
Hotel Type
Hotel Group
Hotel Rule
Hotel Tag
Room Type
Availability
Rate Plan
Provider
Comment
Reviews
Setting
System
Pattern
List view · Create form · Edit form · Delete with confirmation · Validation. Same shape across all 23 modules.
09 / 22
Notes: Track two — Admin CRUD. Twenty-three CRUD modules, one per database table. Each one needs list view, create form, edit form, delete with confirmation, and validation. We standardize the interface so every admin page feels the same. This track lights up incrementally as each table lands — Hotel CRUD goes live the day Hotel DB is ready.

## Slide 10
HOTEL PLATFORM / SECTION 2
— TRACK TWO
Admin CRUD layer.
Facility
Group_Facility
Facility_Hotel
Tag
Location
Landmark
Category
Banner
Promotion
QA
User
Member
Reviews
System
Pattern
List view · Create form · Edit form · Delete with confirmation · Validation. Same shape across all 23 modules.
Comment
Setting
10 / 22
Notes: Track two — Admin CRUD. Twenty-three CRUD modules, one per database table. Each one needs list view, create form, edit form, delete with confirmation, and validation. We standardize the interface so every admin page feels the same. This track lights up incrementally as each table lands — Hotel CRUD goes live the day Hotel DB is ready.

## Slide 11
HOTEL PLATFORM / SECTION 2
— CRUD PHASING
CRUD ships with its tables.
Each CRUD module follows its underlying schema by one week. Ops gets a usable admin tool per domain as soon as it's seeded.
P1 · Wk 1 – 2
Hotel CRUD
Hotel · Type · Group Rule · Tag
5 MODULES
P2 · Wk 3 – 4
Inventory CRUD
Room Type · Availability Rate Plan · Provider
4 MODULES
P3 · Wk 1 – 2
Facility & Geo CRUD
Facility · Group · Pivot · Tag Location · Landmark · Category
7 MODULES
P4 · Wk 1 – 2
Marketing & System CRUD
Banner · Promotion · QA User · Member · Comment Setting
7 MODULES
11 / 22
Notes: How we sequence the CRUD work. We bundle CRUD modules in the same phases as their underlying tables — Hotel CRUD with Hotel DB, Room CRUD with Room DB, and so on. The advantage: the operations team gets a usable admin tool for each domain as soon as the table is migrated. They start seeding real data while we build the next phase. By the time phase four DBs land, the ops team has been live for weeks.

## Slide 12
HOTEL PLATFORM / SECTION 3
— SECTION THREE
Frontend component library.
Thirty-three components grouped by surface. Built bottom-up — each piece testable in isolation before assembly.
Home & Shared
Header, footer, breadcrumb, hero, banner, hotel/city cards, search inputs.
12 COMPONENTS
Hotel Detail
Header section, gallery, room cards, reviews, accordions, sidebars.
11 COMPONENTS
Search Results
Filter sidebar, result cards, sort bar, infinite scroll, shimmers.
10 COMPONENTS
12 / 22
Notes: Track three — Frontend Component library. Thirty-three components, grouped by where they live. Site-wide chrome — header, footer, breadcrumb. Home page surfaces — hero, banners, hotel and city cards, sliders, search box pieces. Hotel detail page — gallery, room cards, reviews, rules accordion, sidebar. Search results page — filter sidebar, result cards, sort bar, infinite scroll, shimmers. We build the library bottom-up so individual pieces are testable in isolation before assembly.

## Slide 13
HOTEL PLATFORM / SECTION 3
— COMPONENT GROUP 1
Home & shared.
Site-wide chrome plus the homepage building blocks. Most ship first — they're reused across pages.
Header
Site-wide top bar — logo, nav, account.
Footer
Quick links, trust marks, contact info.
Breadcrumb
Hierarchical position indicator.
Tab List
Switch between flight / hotel / tour search.
Hero Section
Large media area; search box overlay.
Banner
Static or animated promo placements.
Select Box
Dropdown for cities, hotels, types.
Date Picker
Check-in / check-out range selector.
Guest Selector
Adults, children, infants, rooms.
Hotel Card
Image + summary for grid listings.
City Card
Destination promo card.
Quick Links Card
Phone sales, support shortcuts.
Section Title
List and slider section headings.
Slider
Horizontal carousel for promos.
Article Section
SEO-oriented long-form block.
13 / 22
Notes: Home page and shared components. Eleven components. The site shell — header, footer, breadcrumb. Hero section with the search widget on top. Tab list, select box, date picker, and guest selector together form the search box. Then the marketing surfaces — banner, hotel card, city card, quick links card, slider, section title, article block. Most of these are reusable across pages, so they ship first.

## Slide 14
HOTEL PLATFORM / SECTION 3
— COMPONENT GROUP 2
Hotel detail page.
Single-hotel surface — the core conversion page. Reuses search widgets inside the booking sidebar.
Hotel Header
Name, stars, address, share buttons.
Sticky Page Nav
In-page nav — sticks on scroll.
Image Gallery
Grid or carousel of hotel photos.
Room Card
Per-room details, capacity, price.
Facility Item
Single amenity row with icon.
Quick Info Sidebar
Summary stats, map, key features.
Booking Widget Sidebar
Date picker + check rooms button.
Rating Bar
Per-criterion review bars.
Reviews Section
Aggregate score, tags, rating bars.
Accordion Item
Collapsible content block.
Policies Section
Rules, check-in times, cancellation.
14 / 22
Notes: Hotel detail page components. Eleven components specific to the single-hotel view. Header section with name, stars, address. Sticky in-page nav. Image gallery. Room cards. Facility items. The quick info sidebar. The booking widget sidebar with date picker and search button. Rating bars and the reviews section. Accordion items for the rules and about sections. Policies section. These build on the shared library — the search widget gets reused inside the booking sidebar, for instance.

## Slide 15
— COMPONENT GROUP 3
Search results page.
The result card is the most-viewed surface in the product — it gets the most design and performance attention.
Top Search Widget
Inline filter changes — no page reload.
Filter Sidebar
Price, stars, amenities, more.
Quick Filter Tags
Common filters as clickable chips.
Hotel Result Card
Image, name, address, score, price, CTA.
Sort & Summary Bar
Result count + sort dropdown.
Infinite Scroll Loader
Auto-load more results on scroll.
Shimmer
Skeleton animation while loading.
SEO Content Block
Bottom-of-page descriptive content.
Result card render time is the perf budget anchor. Target sub-50ms for 25 cards.
15 / 22
HOTEL PLATFORM / SECTION 3
Notes: Search results page components. Ten components. The top search widget for filter changes without leaving the page. Filter sidebar with all the criteria — price, stars, amenities. Quick filter tags for the common cases. The hotel result card — the most-viewed surface in the product. Sort and summary bar. Infinite scroll loader and shimmers for the loading states. SEO content block at the bottom. We treat the result card as the primary surface — it gets the most design and performance attention.

## Slide 16
HOTEL PLATFORM / SECTION 3
— COMPONENT
Frontend Component
G1 · Wk 1 – 2
Home & shared
15 COMPONENT
G2 · Wk 3 – 4
Hotel detail page
11 COMPONENT
G3 · Wk 3 – 4
Search results page
8 COMPONENT
A frontend component is a reusable UI element responsible for displaying data and handling user interactions within an application. It encapsulates both presentation and behavior to keep the interface modular and maintainable
16 / 22
Notes: How we sequence the CRUD work. We bundle CRUD modules in the same phases as their underlying tables — Hotel CRUD with Hotel DB, Room CRUD with Room DB, and so on. The advantage: the operations team gets a usable admin tool for each domain as soon as the table is migrated. They start seeding real data while we build the next phase. By the time phase four DBs land, the ops team has been live for weeks.

## Slide 17
HOTEL PLATFORM / SECTION 4
— SECTION FOUR
Public APIs.
Nineteen read endpoints feeding the public site. Unblock as the underlying tables seed up.
— HOTEL DETAIL · 7
Hotel Details
Hotel Images
Hotel Facilities
Hotel Rules
Hotel Rooms
Hotel Comments
Hotel Seo
17 / 22
Notes: Track four — Public APIs. Nineteen endpoints feeding the public website. Hotel detail APIs cover details, images, facilities, rules, rooms, comments, and SEO. Search APIs cover suggestion, filters, hotel list, and city search. Discovery APIs cover special offers, popular hotels, popular domestic destinations, and popular foreign destinations. Plus banners and SEO content. Most of these read from the schema we built in track one — so they unblock as soon as the underlying tables are seeded.

## Slide 18
HOTEL PLATFORM / SECTION 4
— SECTION FOUR
Public APIs.
Nineteen read endpoints feeding the public site. Unblock as the underlying tables seed up.
— SEARCH · 5
Search Suggestion
Search Filters
Search Hotel-list
Search By-city
Search Seo
18 / 22
Notes: Track four — Public APIs. Nineteen endpoints feeding the public website. Hotel detail APIs cover details, images, facilities, rules, rooms, comments, and SEO. Search APIs cover suggestion, filters, hotel list, and city search. Discovery APIs cover special offers, popular hotels, popular domestic destinations, and popular foreign destinations. Plus banners and SEO content. Most of these read from the schema we built in track one — so they unblock as soon as the underlying tables are seeded.

## Slide 19
HOTEL PLATFORM / SECTION 4
— SECTION FOUR
Public APIs.
Nineteen read endpoints feeding the public site. Unblock as the underlying tables seed up.
— DISCOVERY · 7
Special Offers
Popular Hotels
Popular Destinations
Popular Foreign
Banners
Seo Content
Seo Content City
19 / 22
Notes: Track four — Public APIs. Nineteen endpoints feeding the public website. Hotel detail APIs cover details, images, facilities, rules, rooms, comments, and SEO. Search APIs cover suggestion, filters, hotel list, and city search. Discovery APIs cover special offers, popular hotels, popular domestic destinations, and popular foreign destinations. Plus banners and SEO content. Most of these read from the schema we built in track one — so they unblock as soon as the underlying tables are seeded.

## Slide 20
HOTEL PLATFORM / SECTION 4
— COMPONENT
P1 · Wk 1 – 2
7 ENDPOINT
P2 · Wk 1 – 2
SEARCH
5 ENDPOINT
P3 · Wk 1 – 2
7 ENDPOINT
Nineteen read endpoints feeding the public site. Unblock as the underlying tables seed up.
Public APIs.
HOTEL DETAILS
DISCOVERY
20 / 22
Notes: How we sequence the CRUD work. We bundle CRUD modules in the same phases as their underlying tables — Hotel CRUD with Hotel DB, Room CRUD with Room DB, and so on. The advantage: the operations team gets a usable admin tool for each domain as soon as the table is migrated. They start seeding real data while we build the next phase. By the time phase four DBs land, the ops team has been live for weeks.

## Slide 21
HOTEL PLATFORM / SECTION 5
— SECTION FIVE
Page integration.
Three page-level deliverables. Pure assembly — components plus APIs plus routing. Last track to start.
Home Page
Integrates public discovery APIs into the homepage layout. Routing and SEO setup.
WK 1
Search Results Page
Filter state in URL. Wires search APIs to the filter sidebar and result cards.
WK 1
Single Hotel Page
Wires hotel detail APIs into the detail layout. The conversion surface.
WK 1
21 / 22
Notes: Track five — Page Integration. The final track, three deliverables. Home page integrates the public APIs into the homepage layout with routing. Search results page does the same for the search flow with filter state in the URL. Single hotel page wires the detail APIs into the hotel detail layout. This track only starts once the components in track three and the APIs in track four are ready — it's pure assembly and routing.

## Slide 22
HOTEL PLATFORM
— CLOSE
Sequencing & dependencies.
S1
Database Schema
Wk 5 – 6
S2
Admin CRUD
Wk 6 – 10
S3
Frontend Library
Wk 7 – 10
S4
Public APIs
Wk 3 – 6
S5
Page Integration
Wk 3 – 6
23
TABLES · CRUD
33
FE COMPONENTS
19
PUBLIC APIS
27 – 38 Wk
10 – 16 FRONTEND.
17 – 28 BACKEND
22 / 22
Notes: Putting it all together. Track one is the trunk — phase one DBs land first, everything cascades from there. Track two CRUD ships in lockstep with track one. Track three frontend components run in parallel from day one — they don't depend on the database. Track four APIs unblock as the underlying tables seed up. Track five page integration is last, pulling together everything from the other tracks. Realistic timeline: ten to twelve weeks for the full build with two backend engineers and two frontend engineers. Questions?